## Task Tracker
Step | Phase | Task | Description | Status | What Exists Today | Owner | Action Needed
Phase 1 — Data Foundation
1 | Data | Historical poll data | Download Sonntagsfrage tables from Wahlrecht.de. Parse into raw dataframe. Save to disk. | Done | Scraper in scraping/scrapers.py fetches all institutes. CSVs for 8 pollsters already in web/public/polling_data/. | N/A | None — complete.
2 | Data | Clean into canonical schema | Standardize columns, parse dates, normalize pollster names, generate dedup hashes. Output as polls.csv. | Partial | scraping/utils.py cleans percentages, dates, column names. UUIDs added. But no SHA-256 dedup hashes, no unified polls.csv, vote-share-sum validation not enforced. | Claude / Merlin | Add SHA-256 hash column. Create a single merged polls.csv. Add vote-share-sum check (95-105%).
3 | Data | Election results & pollster registry | Compile results.csv (Zweitstimme 2005-2025) and pollsters.csv. Cross-check coverage. | Partial | estimation/dta/processed/ has election results CSVs. data_cleaning.R processes raw constituency data. But 2025 election is missing. No pollsters.csv registry file. | Claude / Merlin | Add Feb 2025 election results. Create pollsters.csv with methodology and active status per firm.
Phase 2 — Model (Prototype)
4 | Model | Baseline Stan model | Minimal Stan model: random walk latent support, noisy poll observations, election anchors. Compile with cmdstanr. | Done | benchmark_forecast.stan implements random walk on log-odds, multinomial likelihood, sigmoid party emergence, LFO cross-validation. gp_model.stan is a richer alternative with GPs + splines. | N/A | None — exceeds spec (two models available).
5 | Model | Full fitting script | Write fit.R: reads CSVs, constructs Stan data list, runs sampler, saves fit. Handle date-to-index mapping and compositional constraint. | Partial | estimation/main.R does this but only loads Allensbach (Forsa/INSA commented out). Hardcoded setwd() path. No CLI interface. | Claude / Merlin | Uncomment and integrate all 8 pollsters. Remove hardcoded setwd(). Make the script runnable from project root.
6 | Model | Retrodictive check | Fit using only polls up to 7 days before each past election. Compare posterior to actual results. Check interval calibration. | Partial | main.R has extract_model_diagnostics() with ELPD, MSE, coverage by horizon, PIT values. LFO cutoff built into Stan model. But no standalone notebook documenting results. | Merlin | Run the retrodictive check with all pollsters, document results in a short notebook or report.
7 | Model | Posterior export to JSON | Write export.R: outputs current_forecast.json, forecast_timeseries.json, and polls.json for the frontend. | Partial | save_daily_vote_shares() in utils.R exports to CSV (daily_vote_shares.csv). But format is CSV not JSON, and it does not produce the three separate JSON files the frontend needs. | Claude / Merlin | Write export function producing JSON outputs: current_forecast.json, forecast_timeseries.json, polls.json.
Phase 3 — Frontend
8 | Frontend | Static site skeleton | index.html with CSS, party color palette, responsive layout, navigation. Deploy to hosting. | Done | web/public/ has index.html, about.html, forecasts.html, docs/, CSS with party colors, responsive nav, fixed header. Vercel config present. | N/A | None — structure is in place.
9 | Frontend | Time series chart | D3 chart: one line per party with shaded 90% credible interval bands. Poll dots as scatter overlay. | Partial | visualization.js has D3 chart with rolling averages for 3 parties (CDU/CSU, SPD, FDP). Has brush zoom and tooltips. But no credible intervals, missing parties (Gruene, AfD, Linke, BSW), reads raw CSVs not model output. | Claude / Merlin | Rewrite visualization.js to consume model JSON output. Add all parties. Add shaded credible interval bands.
10 | Frontend | Current estimate display | Summary panel: each party median and 90% interval. Last updated timestamp and poll count. | Not started | Nothing exists for this. | Claude / Merlin | Build summary panel component below the chart reading from current_forecast.json.
11 | Frontend | Methodology page | ~800 words explaining model, uncertainty intervals, data sources, planned improvements. Link to repo. | Not started | web/docs/ has an R Markdown skeleton and bibliography but no actual methodology content. | Merlin / Claude | Write methodology page content (~800 words, non-statistician readable).
Phase 4 — Automation
12 | Automation | Wahlrecht.de scraper | Python script: fetch page, parse table, compare hashes, append new rows. Handle errors gracefully. | Partial | scraping/scrapers.py does full scraping and parsing. But no hash-based incremental detection — it re-scrapes everything each time. | Claude / Merlin | Add hash-based dedup so only new polls are appended. Add error handling for network failures.
13 | Automation | Validation logic | validate.py with structural checks, dedup, anomaly flagging. Unit tests. | Not started | No validate.py exists. No unit tests for data validation. | Claude / Merlin | Create validate.py: vote-share-sum check, sample-size range, date validity, hash dedup, 3-sigma anomaly flagging. Write tests.
14 | Automation | Pipeline CLI | pipeline.py with subcommands: scrape, validate, fit, export, run. Early exit if no new polls. | Not started | main.py just calls scrape_all_polling_houses(). No subcommands, no fit/export integration. | Claude / Merlin | Rewrite main.py / pipeline.py with argparse subcommands orchestrating the full pipeline.
15 | Automation | GitHub Actions workflow | Cron workflow every 6 hours. Install R + Python deps. Run pipeline. Commit and push if new data. | Not started | No .github/workflows/ directory exists. | Claude / Merlin | Create update.yml with cron schedule, R/Python setup, pipeline execution, conditional commit.
16 | Automation | Anomaly notifications | Telegram bot or email notification on flagged polls. Manual approval via JSON allowlist. | Not started | Nothing exists for this. | Merlin | Choose notification channel (Telegram/email). Implement flagging + approval flow.
Phase 5 — Launch
17 | Launch | Domain and polish | Register domain, configure DNS, add Open Graph tags, test mobile, proof methodology page. | Not started | Vercel config exists (web/vercel.json) but no custom domain or OG tags. | Merlin | Register domain. Add OG meta tags. Verify mobile layout. Confirm pipeline stability.
18 | Launch | Soft launch | Write ~500 word launch post. Share to polisci and forecasting communities. | Not started | Nothing exists for this. | Merlin | Write launch post. Identify target communities (polisci Twitter/Bluesky, forecasting forums).

## Summary
Metric | Count | % of Total
Total tasks | 18
Done | 3 | 17%
Partial | 7 | 39%
Not started | 8 | 44%